**FY2019 Continuum of Care Program Competition Timeline**

QUESTIONS: Contact Shavon Moore at 214-605-0108 or shavon.moore@mdhadallas.org

***MDHA will update this calendar throughout the CoC competition process Latest Update: 07-17-2019***

mdhadallas.org/2019-nofa-coc-program-grant-competition/

|  |  |  |
| --- | --- | --- |
| **DATE** | **TASK** | **LOCATION** |

|  |  |  |
| --- | --- | --- |
| **April** | | |
| Monday, April 29 | MDHA releases Intent to Apply | Sent via Constant Contact and posted on MDHA’s website |
| **May** | | |
| Friday, May 3 | Intent to Apply due | Emailed to Shavon Moore |
| **July** | | |
| Wednesday, July 3 | HUD Issues FY 2019 CoC NOFA | <https://www.hudexchange.info/resource/5842/fy-2019-coc-program-nofa/> |
| Monday, July 15 | MDHA issues CoC NOFA FY 2019 Timeline | Sent electronically via Constant Contact & listed on MDHA’s website |
| Wednesday, July 17 | MDHA issues NOFA Score Card and Priorities for public comment (Public comment period July 17-19) | Sent electronically via Constant Contact & listed on MDHA’s website |
| Monday, July 22 – Friday,  July 26  *Submit Help Ticket* | MDHA provides technical assistance for APR clean up (Optional) |  |
| Monday, July 22 | MDHA issues NOFA Application for FY2019 CoC Program Grant for Renewal and New Projects | Posted on MDHA’s website |
| Tuesday, July 23 | Final draft of Score Card and NOFA Priorities presented to CoC Assembly | CoC General Assembly Meeting  9:00 a.m.  United Way |
| Friday, July 26 | MDHA sends Score Card and NOFA Priorities to CoC board for final approval | Meeting closed to general public  Results will be posted to MDHA’s website and sent via Constant Contact |
| **August** | | |
| Thursday, August 1 | MDHA FY2019 CoC Application Workshop  MDHA posts Score Cards for all projects | *Location to be determined*.  Score Cards will be uploaded to Base Camp |
| Monday, August 5, 2019 | Final APRs due to MDHA | Uploaded to Base Camp |
| Wednesday, August 14 | MDHA will issue final Score Cards and APRs for use with NOFA application | Uploaded to Base Camp |
| Friday, August 16 | FY2019 CoC Local Competition Project Applications **DEADLINE** (in eSNAPS and narratives submission to MDHA) | Uploaded to Base Camp |
| Friday, August 23 | PRAC Application Handoff and Instructional Meeting  Applicants can attend. | *Location to be determined*. |
| Friday, August 30 | PRAC Prioritization and Funding Decisions Meeting.  Applicants notified of decision following the meeting | Closed meeting  Emailed to applicants |
| **September** | | |
| Tuesday, September 3 – Wednesday, September 4 | Grievance Committee available for grievances by appointment only | Contact Shavon to schedule |
| Thursday, September 5 | Publication of the FY2019 CoC Program Grant Project Priority List | Posted on MDHA’s website |
| Friday, September 6 | CoC Board approves Priority Ranking as recommended by PRAC | Closed meeting  Priority Listing will be posted on MDHA’s website |
| Friday, September 20 | MDHA Website posting of the CoC Collaborative Application | Posted on MDHA’s website |
| Monday, September 30  8:00 p.m. | HUD Deadline for Collaborative Application | Submitted via eSNAPS |